## Sheet1
Field | Description | Example
Report Title | Test Closure Report for [Project Name] - [Version/Release] | Test Closure Report for MyFantasticApp v1.2
Report ID | Unique Identifier (e.g., YYYY-MM-DD-TestId) | 2024-07-12-TCReport1
Date | Date the report is generated | 2024-07-12
Project Name | Name of the project being tested | MyFantasticApp
Test Phase | Testing phase (e.g., Functional Testing, Integration Testing) | Functional Testing
Testing Start Date | Date testing began | 2024-07-01
Testing End Date | Date testing concluded | 2024-07-11
Total Test Cases Executed | Number of test cases run | 100
Test Case Pass Rate | Percentage of test cases that passed | 85%
Test Case Fail Rate | Percentage of test cases that failed | 15%
Total Defects Identified | Number of defects found during testing | 12
Open Defects | Number of defects still outstanding | 3
Closed Defects | Number of defects resolved | 9
Scope of Testing | Briefly describe what was tested in this phase | All core functionalities of the application
Variations from Test Plan | Mention any deviations from the original plan | Login functionality required additional testing due to last-minute UI changes
Testing Tools | List tools used for testing (e.g., Selenium, Jira) | Selenium WebDriver, Postman
Defect Severity (Critical) | Number of critical defects identified | 1
Defect Severity (High) | Number of high-severity defects identified | 2
Defect Severity (Medium) | Number of medium-severity defects identified | 4
Defect Severity (Low) | Number of low-severity defects identified | 5
Open Defect List | Include columns for Defect ID, Description, Severity, Priority, and Owner | (See next row for example data)
Open Defect (Example) |  | Defect-001
Exit Criteria Met | Indicate if all pre-defined exit criteria were achieved (Yes/No) | Yes
Testing Environment | Briefly describe the testing environment (hardware, software, configuration)
Lessons Learned | List key takeaways and areas for improvement | More automation scripts could improve testing efficiency
Approvals | Include space for signatures from QA Lead and optional Project Manager